## Summary
Grand Summary
Rehabilitation of R14 Balti – Sarateni Road
Lot 2: km 43+000 to km 61+000, km 64+370 to km 66+657 |  |  |  | Contract 1 | Contract 2 | Contract 3
|  |  |  | (km44+32-km66+67) | km 10,78-km26,6 | km26,6-km66+67)
General Summary |  |  | Amount
Bill No. 1 | General Items |  | 0 | #REF! | #REF! | 0 | #REF!
| Lucrari de pregatire a santierului | [5 empty] | 0
Bill No. 2 | Site Clearance |  | 0 | #REF! | #REF! | #REF! | #REF!
| Terasamente | [5 empty] | 0
Bill No. 3 | Earthworks |  | 0 | #REF! | #REF! | #REF! | #REF!
| Sistem rutier | [5 empty] | 0
Bill No. 4 | Pavement |  | 0 | #REF! | #REF! | #REF! | #REF!
| Evacuarea apelor | [5 empty] | 0
Bill No. 5. | Drainage |  | 0 | #REF! | #REF! | #REF! | #REF!
| Poduri | [5 empty] | 0
Bill No. 6 | Bridgeworks |  | 0 | #REF! | #REF! | #REF! | #REF!
| Masuri contra deformaţiilor de teren | [5 empty] | 0
Bill No. 7 | Slip Remedial Works |  | Not Used | Not Used | Not Used | #REF! | #REF!
| Indicatoare, marcaje si parapeti rutiere | [5 empty] | 0
Bill No. 8 | Signs, Markings and Guardrail |  | 0 | #REF! | #REF! | #REF! | #REF!
| Drumuri laterale, Benzi de accelerare, decelerare, Locuri staţionare, etc | [5 empty] | 0
Bill No. 9 | Miscellaneous Works |  | 0 | #REF! | #REF! | #REF! | #REF!
0
Bill No. 10 | Dayworks |  | 0 | 0 | 0 | 0 | 0
Subtotal of Bills |  |  | 0 | #REF! | #REF! | #REF!
PROVISIONAL SUM FOR CONTINGENCIES |  |  | 2000000 | #REF! | #REF! | #REF!
Total Estimated Price |  | EUROS | 2000000 | #REF! | #REF! | #REF!

## 1. General Items
1. General Items
Item | Specn. | Description | Quantity | Unit | Rate | Amount
No | Ref.
Nr | Codul | Descrition | Cantitate | U/m
crt | articolului
1 | 2 | 3 | 4 | 5 | 6 | 7
1.01 | 00401 | Provide, Furnish and equip Contract Office | 1 | Sum |  | 0
1.02 | 00402 | Maintain Contract Office | 24 | Months |  | 0
1.03 | 00501 | Provide and Equip Site Laboratory and Office | 1 | Sum |  | 0
1.04 | 00701 | Manage and maintain traffic throughout the period of he Works | 1 | Sum |  | 0
1.05 | 00801 | Provide Insurances | 1 | Sum |  | 0
1.06 | 00802 | Provide Performance Bond | 1 | Sum |  | 0
1.07 | 01601 | Compliaance with Environmental Menagement Plan Reguirements | 1 | Sum |  | 0
|  | Total General Items to Summary |  |  |  | 0

## 2,Lucr de preg
2. Site Clearing Off
Item | Specn. | Наименование работ | Description | Unit | Quantity | Rate | Amount
No | Ref.
0 | 1 | 2 | 2 | 3 | 4 | 5 | 6
2.01 | 10101 | Восстановление и разбивка осей сооружений | Surveying and setting out works | km | 23.7 |  | 0
2.02 | 10201 | Корчевка деревьев до 150 мм и кустарника | Clearing brush, undergrowth and vegetation and removal of topsoil | Sq.m | 5000 |  | 0
2.03 | 10203 | Корчевка деревьев > 150 мм | Trees clearance | No | 45 |  | 0
2.04 | 10305 | Разборка металлического ограждения | Remove cable type Guard Rail | Lin.m | 3215 |  | 0
2.05 | 10306 | Разборка существующего бордюра | Removal of existing kerbs | Lin.m | 330 |  | 0
2.06 | 10301 | Разборка существующих дорожных знаков | Traffic signs removal | No | 7 |  | 0
2.07 | 10307 | Разборка километровых знаков | Removal of kilometre posts and dispose | No | 21 |  | 0
2.08 | 10501 | Устройство объездного пути (ПК248+90-ПК250+13) | Provide Diversion Road | Lin.m | 802 |  | 0
|  |  | Total site clearance To Summary |  |  |  | 0
|  |  | Total site clearance To Summary |  |  |  | 0

## 3, Terasamente
3. Earthworks
Item | Specn. | Description | Unit | Quantity | Rate | Amount
No | Ref.
0 | 1 | 2 | 3 | 4 | 5 | 6
3.01 | 20101 | Regrade Shoulders | Sq.m | 82760 |  | 0
3.02 | 20104 | Any type of excavations, including slipped soil and benches with material transported to embankment or to spoil. | Cu.m | 100120 |  | 0
3.03 | 20104A | Excavation of waste concrete of culvert demolition and transported to embankment or to spoil. | Cu.m | 20.9 |  | 0
3.04 | 20106 | Shape and compact subgrade | Sq.m | 468174 |  | 0
3.05 | 20401 | Placing of topsoil in nominal 150mm layer | Cu.m | 52458 |  | 0
3.06 | 20403 | Trimming and shaping of slopes | Sq.m | 105320 |  | 0
3.07 | 20201 | Excavation of Channels and drains outside the road cross section | Cu.m | 540 |  | 0
|  | Total To Earthworks Summary |  |  |  | 0

## 4, Sist Rut
4. Road Pavement
Item No | Specn. Ref | Description | Unit | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
4.01 | 31101 | Pothole patching with asphalt | Tonnes | 110 |  | 0
4.02 | 31201 | Cleaning and grouting of cracks | Lin.m | 46866 |  | 0
4.03 | 30201 | Regulating course of asphalt mixture | Tonnes | 29847 |  | 0
4.04 | 30202 | Milling of existing asphalt pavement | Tonnes | 5310 |  | 0
4.05 | 30301 | Sand drainage layer | Cu.m | 28100 |  | 0
4.06 | 30302 | Subbase courses of ballast or crushed limestone | Cu.m | 12490 |  | 0
4.07 | 30303 | Base courses of crushed granite | Cu.m | 12490 |  | 0
4.08 | 30304 | Excavation and disposal or reuse of existing pavement material | Cu.m | 2466 |  | 0
4.09 | 30401 | Prime-coat using cutback bitumen 0.3l/sq.m | Litres | 146700 |  | 0
4.10 | 30402 | Tack coat using cutback bitumen or bituminous emulsion 0.6l/sq.m | Litres | 23800 |  | 0
4.11 | 30501 | Wearing course of asphalt concrete from fine grained dense asphalt Type A M1 thickness 40mm | Sq.m | 236942 |  | 0
4.12 | 30503 | Base course made of fine grained porous asphalt concrete M1, thickness 40mm | Sq.m | 12957 |  | 0
4.13 | 30504 | Base course made of fine grained porous asphalt concrete M1 Thickness 60mm | Sq.m | 41840 |  | 0
4.14 | 30505 | Base course made of coarse grained porous asphalt concrete M1 thickness 70mm | Sq.m | 3996 |  | 0
4.15 | 30506 | Base course made of coarse grained porous asphalt concrete e M1 thickness 85mm | Sq.m | 41840 |  | 0
4.16 | 30601 | Strengthening of the shoulders with crushed stone M300 shoulder thickness 150mm | Sq.m | 40590 |  | 0
4.17 | 90201 | Geotextile fabric Type 1 in reinforcement to Embankment | Sq.m | 63421 |  | 0
4.18 | 90202 | Geotextile fabric Type 2 as a filter membrane . | Sq.m | 236942 |  | 0
|  | Total To Pavement Summary |  |  |  | 0

## 5,Evacuarea apelor
5. Drainage
Item No | Specn. Ref | Description | Unit | Quantity | Rate | Amount
0 | 1 | 2 | 2 | 4 | 5 | 6
5.01 | 50101 | Removal of Culvert Inlet or Outlet | Number | 12 |  | 0
5.02 | 50102 | Removal of existing culvert barrel | Lin.m | 35 |  | 0
5.03 | 50103A | Construction of culvert inlets and outlets to pipe culverts (pipe diameter to be stated) m | Number | 20 |  | 0
5.04 | 50105A | Construction of new pipe culverts (pipe diameter to be stated) | Lin.m | 100 |  | 0
5.05 | 50107A | Extension of pipe culverts (pipe diameter to be stated) m type TN | Lin. metre | 10 |  | 0
5.06 | 50109 | Additional protection works at inlets and outlets | Sq.m | 2032 |  | 0
5.07 | 50111 | Construction of drop inlets to pipe culverts of any diameter | Number | 1 |  | 0
5.08 | 50202 | Cleaning of existing culverts | Lin.m | 110 |  | 0
5.09 | 50301 | New construction of Triangular section chute or spillway on embankment slope 0,6 wide x0.3 deep or other approved section made of precast concrete units or cast in situ | Lin.m | 126 |  | 0
5.10 | 50302 | New construction of Lined side drain or waterway Type 1 with precast concrete units and/or concrete cast in situ. | Lin.m | 3490 |  | 0
5.11 | 50303 | New construction of Lined side drain or waterway Type 2 with precast concrete units and/or concrete cast in situ including anchor blocks. | Lin.m | 59 |  | 0
5.12 | 50305 | Construct chute entry gully, single sided entry | Number | 18 |  | 0
5.13 | 30601 | Consolidation of new trapezoidal side ditch with grass seeding | Lin.m | 12501 |  | 0
5.14 | 50303A | New construction of Lined side drain or waterway Type 3 with precast concrete units and/or concrete cast in situ including anchor blocks. | Lin.m | 140 |  | 0
5.15 | 50401 | Miscellaneous minor concrete structures | Cu.m | 4.4 |  | 0
|  | Total Drainage To Summary |  |  |  | 0

## 6. Poduri
6. Bridge works Summary
|  | Location | Amount
|  | 6.10. Bridge Repairs km 44 + 744 | 0
|  | 6.11. Bridge Repairs km 46 + 863 | 0
|  | 6.12. Bridge Repairs km 49+ 330 | 0
|  | 6.13. Bridge Repairs km 52+ 012 | 0
|  | 6.14. Bridge Repairs km 53+ 969 | 0
|  | 6.15. Bridge Repairs km 59+ 233 | 0
|  | 6.16. Bridge Repairs km 64+ 756 | 0
|  | Total Bridge works to Summary | 0
6.10. Structure at km 44 + 744
Item No. | Specn. Ref | Description | Units | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
6.10.01 | 40101 | Minor repair of the infrasructure and superstructure elements with reinforced concrete | Cu.m | 75.6 |  | 0
6.10.02 | 40103 | Minor repair of the infrasructure and superstructure elements with mortar with polimer | Cu.m | 0.33 |  | 0
6.10.03 | 40108 | Painting of the visible surfaces of the infrastructure and superstructure elements using liquid Suspension of cement with polymers | Sq.m | 318.8 |  | 0
6.10.04 | 40109 | Piles factory manufacture, transporting and installation on the site | Cu.m | 27.5 |  | 0
6.10.05 | 40204 | Hand drilling in reinforced concrete | Lin.m | 98.3 |  | 0
6.10.06 | 40205 | Production and installation of steel parts and reinforcement | kg | 757 |  | 0
6.10.07 | 40502 | Provision of approach slabs at existing bridges, length 4,0 metres, where there is no existing approach slab | Sq. m | 74 |  | 0
6.10.08 | 40702 | Construction of expanssion joints to new decks (deck length less than 12 metres) | Lin.m | 122.46 |  | 0
6.10.09 | 40801 | Waterproofing to existing bridge decks | Sq.m | 93.6 |  | 0
6.10.10 | 40802 | Waterproofing to new bridge decks | Sq.m | 294.75 |  | 0
6.10.11 | 40901 | Execution of metal safety parapets on the bridge deck | Lin.m | 44 |  | 0
6.10.12 | 40902 | Execution of metal safety parapets with stub foundation on the bridge deck | Lin.m | 20.8 |  | 0
6.10.13 | 40903 | Execution of metal safety parapets on the approach embankment | Lin.m | 92 |  | 0
6.10.14 | 40904 | Painting of the poles of metal safety parapets | Lin.m | 156.8 |  | 0
6.10.15 | 41203 | Protection to approach embankment slopes with reinforced concrete of 12 cm thicknes over a layer of crushed stone of 10 cm thickness | Sq. m | 128.3 |  | 0
6.10.16 | 41301 | Laying of 70 mm of fine asphalt Type A, M-I, on the carriageway of the bridge deck in two layers | Sq.m | 161.87 |  | 0
6.10.17 | 41302 | Laying of 40mm of fine asphalt Type A, M-I, on the walkways | Sq.m | 36.55 |  | 0
6.10.18 | 41501 | Provision and installation of rubber bearing pads | Unit | 24 |  | 0
6.10.19 | 41801 | Demolishing of reinforced concrete parapeţs of the bridge or embankment | Cu.m | 1.99 |  | 0
6.10.20 | 41802 | Dismantling of the metal pedestrian parapets | Lin.m | 77 |  | 0
6.10.21 | 41804 | Removal of the asphalt pavement on the bridge deck | Sq. m | 177.5 |  | 0
| Total to Bridges Summary |  |  |  |  | 0
6.11. Structure at km 46 + 863
Item No. | Specn. Ref | Description | Units | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
6.11.01 | 40101 | Minor repair of the infrasructure and superstructure elements with reinforced concrete | Cu.m | 102.6 |  | 0
6.11.02 | 40103 | Minor repair of the infrasructure and superstructure elements with mortar with polimer | Cu.m | 0.33 |  | 0
6.11.03 | 40108 | Painting of the visible surfaces of the infrastructure and superstructure elements using liquid Suspension of cement with polymers | Sq.m | 318.8 |  | 0
6.11.04 | 40109 | Piles factory manufacture, transporting and installation on the site | Cu.m | 22 |  | 0
6.11.05 | 40204 | Hand drilling in reinforced concrete | Lin.m | 99 |  | 0
6.11.06 | 40205 | Production and installation of steel parts and reinforcement | kg | 757 |  | 0
6.11.07 | 40502 | Provision of approach slabs at existing bridges, length 4,0 metres, where there is no existing approach slab | Sq. m | 74 |  | 0
6.11.08 | 40702 | Construction of expanssion joints to new decks (deck length less than 12 metres) | Lin.m | 102.5 |  | 0
6.11.09 | 40801 | Waterproofing to existing bridge decks | Sq.m | 95.7 |  | 0
6.11.10 | 40802 | Waterproofing to new bridge decks | Sq.m | 300.1 |  | 0
6.11.11 | 40901 | Execution of metal safety parapets on the bridge deck | Lin.m | 44 |  | 0
6.11.12 | 40902 | Execution of metal safety parapets with stub foundation on the bridge deck | Lin.m | 20.8 |  | 0
6.11.13 | 40903 | Execution of metal safety parapets on the approach embankment | Lin.m | 92 |  | 0
6.11.14 | 40904 | Painting of the poles of metal safety parapets | Lin.m | 156.8 |  | 0
6.11.15 | 41203 | Protection to approach embankment slopes with reinforced concrete of 12 cm thicknes over a layer of crushed stone of 10 cm thickness | Sq. m | 146.75 |  | 0
6.11.16 | 41301 | Laying of 70 mm of fine asphalt Type A, M-I, on the carriageway of the bridge deck in two layers | Sq.m | 149.88 |  | 0
6.11.17 | 41302 | Laying of 40mm of fine asphalt Type A, M-I, on the walkways | Sq.m | 51.31 |  | 0
6.11.18 | 41501 | Provision and installation of rubber bearing pads | Unit | 24 |  | 0
6.11.19 | 41801 | Demolishing of reinforced concrete parapeţs of the bridge or embankment | Cu.m | 1.98 |  | 0
6.11.20 | 41802 | Dismantling of the metal pedestrian parapets | Lin.m | 49.5 |  | 0
6.11.21 | 41804 | Removal of the asphalt pavement on the bridge deck | Sq. m | 177.5 |  | 0
| Total to Bridges Summary |  |  |  |  | 0
6.12. Structure at km 49 + 330
Item No. | Specn. Ref | Description | Units | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
6.12.01 | 40101 | Minor repair of the infrasructure and superstructure elements with reinforced concrete | Cu.m | 157.95 |  | 0
6.12.02 | 40103 | Minor repair of the infrasructure and superstructure elements with mortar with polimer | Cu.m | 0.24 |  | 0
6.12.03 | 40108 | Painting of the visible surfaces of the infrastructure and superstructure elements using liquid Suspension of cement with polymers | Sq.m | 227.3 |  | 0
6.12.04 | 40109 | Piles factory manufacture, transporting and installation on the site | Cu.m | 41.56 |  | 0
6.12.05 | 40204 | Hand drilling in reinforced concrete | Lin.m | 88 |  | 0
6.12.06 | 40205 | Production and installation of steel parts and reinforcement | kg | 502 |  | 0
6.12.07 | 40502 | Provision of approach slabs at existing bridges, length 4,0 metres, where there is no existing approach slab | Sq. m | 74 |  | 0
6.12.08 | 40702 | Construction of expanssion joints to new decks (deck length less than 12 metres) | Lin.m | 382.08 |  | 0
6.12.09 | 40801 | Waterproofing to existing bridge decks | Sq.m | 188.4 |  | 0
6.12.10 | 40802 | Waterproofing to new bridge decks | Sq.m | 250.4 |  | 0
6.12.11 | 40901 | Execution of metal safety parapets on the bridge deck | Lin.m | 44 |  | 0
6.12.12 | 40902 | Execution of metal safety parapets with stub foundation on the bridge deck | Lin.m | 16 |  | 0
6.12.13 | 40903 | Execution of metal safety parapets on the approach embankment | Lin.m | 92 |  | 0
6.12.14 | 40904 | Painting of the poles of metal safety parapets | Lin.m | 152 |  | 0
6.12.15 | 41203 | Protection to approach embankment slopes with reinforced concrete of 12 cm thicknes over a layer of crushed stone of 10 cm thickness | Sq. m | 406.3 |  | 0
6.12.16 | 41301 | Laying of 70 mm of fine asphalt Type A, M-I, on the carriageway of the bridge deck in two layers | Sq.m | 125.42 |  | 0
6.12.17 | 41302 | Laying of 40mm of fine asphalt Type A, M-I, on the walkways | Sq.m | 25.82 |  | 0
6.12.18 | 41501 | Provision and installation of rubber bearing pads | Unit | 24 |  | 0
6.12.19 | 41801 | Demolishing of reinforced concrete parapeţs of the bridge or embankment | Cu.m | 1.99 |  | 0
6.12.20 | 41802 | Dismantling of the metal pedestrian parapets | Lin.m | 77 |  | 0
6.12.21 | 41804 | Removal of the asphalt pavement on the bridge deck | Sq. m | 177.5 |  | 0
| Total to Bridges Summary |  |  |  |  | 0
6.13. Structure at km 52 + 012
Item No. | Specn. Ref | Description | Units | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
6.13.01 | 40101 | Minor repair of the infrasructure and superstructure elements with reinforced concrete | Cu.m | 105.84 |  | 0
6.13.02 | 40103 | Minor repair of the infrasructure and superstructure elements with mortar with polimer | Cu.m | 0.33 |  | 0
6.13.03 | 40108 | Painting of the visible surfaces of the infrastructure and superstructure elements using liquid Suspension of cement with polymers | Sq.m | 318.8 |  | 0
6.13.04 | 40109 | Piles factory manufacture, transporting and installation on the site | Cu.m | 543.56 |  | 0
6.13.05 | 40204 | Hand drilling in reinforced concrete | Lin.m | 98.3 |  | 0
6.13.06 | 40205 | Production and installation of steel parts and reinforcement | kg | 917 |  | 0
6.13.07 | 40502 | Provision of approach slabs at existing bridges, length 4,0 metres, where there is no existing approach slab | Sq. m | 74 |  | 0
6.13.08 | 40702 | Construction of expanssion joints to new decks (deck length less than 12 metres) | Lin.m | 123.28 |  | 0
6.13.09 | 40801 | Waterproofing to existing bridge decks | Sq.m | 185 |  | 0
6.13.10 | 40802 | Waterproofing to new bridge decks | Sq.m | 294.75 |  | 0
6.13.11 | 40901 | Execution of metal safety parapets on the bridge deck | Lin.m | 44 |  | 0
6.13.12 | 40902 | Execution of metal safety parapets with stub foundation on the bridge deck | Lin.m | 20.8 |  | 0
6.13.13 | 40903 | Execution of metal safety parapets on the approach embankment | Lin.m | 92 |  | 0
6.13.14 | 40904 | Painting of the poles of metal safety parapets | Lin.m | 156.8 |  | 0
6.13.15 | 41203 | Protection to approach embankment slopes with reinforced concrete of 12 cm thicknes over a layer of crushed stone of 10 cm thickness | Sq. m | 36.6 |  | 0
6.13.16 | 41301 | Laying of 70 mm of fine asphalt Type A, M-I, on the carriageway of the bridge deck in two layers | Sq.m | 161.87 |  | 0
6.13.17 | 41302 | Laying of 40mm of fine asphalt Type A, M-I, on the walkways | Sq.m | 36.55 |  | 0
6.13.18 | 41501 | Provision and installation of rubber bearing pads | Unit | 24 |  | 0
6.13.19 | 41801 | Demolishing of reinforced concrete parapeţs of the bridge or embankment | Cu.m | 1.99 |  | 0
6.13.20 | 41802 | Dismantling of the metal pedestrian parapets | Lin.m | 77 |  | 0
6.13.21 | 41804 | Removal of the asphalt pavement on the bridge deck | Sq. m | 177.5 |  | 0
| Total to Bridges Summary |  |  |  |  | 0
6.14. Structure at km 53 + 969
Item No. | Specn. Ref | Description | Units | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
6.14.01 | 40101 | Minor repair of the infrasructure and superstructure elements with reinforced concrete | Cu.m | 157.21 |  | 0
6.14.02 | 40103 | Minor repair of the infrasructure and superstructure elements with mortar with polimer | Cu.m | 0.24 |  | 0
6.14.03 | 40108 | Painting of the visible surfaces of the infrastructure and superstructure elements using liquid Suspension of cement with polymers | Sq.m | 227.3 |  | 0
6.14.04 | 40109 | Piles factory manufacture, transporting and installation on the site | Cu.m | 41.56 |  | 0
6.14.05 | 40204 | Hand drilling in reinforced concrete | Lin.m | 88 |  | 0
6.14.06 | 40205 | Production and installation of steel parts and reinforcement | kg | 502 |  | 0
6.14.07 | 40502 | Provision of approach slabs at existing bridges, length 4,0 metres, where there is no existing approach slab | Sq. m | 74 |  | 0
6.14.08 | 40702 | Construction of expanssion joints to new decks (deck length less than 12 metres) | Lin.m | 395.58 |  | 0
6.14.09 | 40801 | Waterproofing to existing bridge decks | Sq.m | 188.4 |  | 0
6.14.10 | 40802 | Waterproofing to new bridge decks | Sq.m | 250.4 |  | 0
6.14.11 | 40901 | Execution of metal safety parapets on the bridge deck | Lin.m | 44 |  | 0
6.14.12 | 40902 | Execution of metal safety parapets with stub foundation on the bridge deck | Lin.m | 16 |  | 0
6.14.13 | 40903 | Execution of metal safety parapets on the approach embankment | Lin.m | 92 |  | 0
6.14.14 | 40904 | Painting of the poles of metal safety parapets | Lin.m | 152 |  | 0
6.14.15 | 41203 | Protection to approach embankment slopes with reinforced concrete of 12 cm thicknes over a layer of crushed stone of 10 cm thickness | Sq. m | 425.5 |  | 0
6.14.16 | 41301 | Laying of 70 mm of fine asphalt Type A, M-I, on the carriageway of the bridge deck in two layers | Sq.m | 125.42 |  | 0
6.14.17 | 41302 | Laying of 40mm of fine asphalt Type A, M-I, on the walkways | Sq.m | 25.82 |  | 0
6.14.18 | 41501 | Provision and installation of rubber bearing pads | Unit | 24 |  | 0
6.14.19 | 41804 | Removal of the asphalt pavement on the bridge deck | Sq. m | 198 |  | 0
| Total to Bridges Summary |  |  |  |  | 0
6.15. Structure at km 59 + 233
Item No. | Specn. Ref | Description | Units | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
6.15.01 | 40101 | Minor repair of the infrasructure and superstructure elements with reinforced concrete | Cu.m | 40.24 |  | 0
6.15.02 | 40204 | Hand drilling in reinforced concrete | Lin.m | 88.7 |  | 0
6.15.03 | 40205 | Production and installation of steel parts and reinforcement | kg | 151 |  | 0
6.15.04 | 40502 | Provision of approach slabs at existing bridges, length 4,0 metres, where there is no existing approach slab | Sq. m | 74 |  | 0
6.15.05 | 40702 | Construction of expanssion joints to new decks (deck length less than 12 metres) | Lin.m | 132.88 |  | 0
6.15.06 | 40801 | Waterproofing to existing bridge decks | Sq.m | 44 |  | 0
6.15.07 | 40802 | Waterproofing to new bridge decks | Sq.m | 173.3 |  | 0
6.15.08 | 40901 | Execution of metal safety parapets on the bridge deck | Lin.m | 44 |  | 0
6.15.09 | 40902 | Execution of metal safety parapets with stub foundation on the bridge deck | Lin.m | 7.2 |  | 0
6.15.10 | 40903 | Execution of metal safety parapets on the approach embankment | Lin.m | 76 |  | 0
6.15.11 | 40904 | Painting of the poles of metal safety parapets | Lin.m | 127.2 |  | 0
6.15.12 | 41203 | Protection to approach embankment slopes with reinforced concrete of 12 cm thicknes over a layer of crushed stone of 10 cm thickness | Sq. m | 21.7 |  | 0
6.15.13 | 41301 | Laying of 70 mm of fine asphalt Type A, M-I, on the carriageway of the bridge deck in two layers | Sq.m | 59.94 |  | 0
6.15.14 | 41302 | Laying of 40mm of fine asphalt Type A, M-I, on the walkways | Sq.m | 12.34 |  | 0
6.15.15 | 41801 | Demolishing of reinforced concrete parapet of bridge or embankment | Cu.m | 1.89 |  | 0
6.15.16 | 41804 | Removal of the asphalt pavement on the bridge deck | Sq. m | 156.28 |  | 0
| Total to Bridges Summary |  |  |  |  | 0
6.16. Structure at km 64 + 756
Item No. | Specn. Ref | Description | Units | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
6.16.01 | 40101 | Minor repair of the infrasructure and superstructure elements with reinforced concrete | Cu.m | 635.07 |  | 0
6.16.02 | 40103 | Minor repair of the infrasructure and superstructure elements with mortar with polimer | Cu.m | 0.03 |  | 0
6.16.03 | 40108 | Painting of the visible surfaces of the infrastructure and superstructure elements using liquid Suspension of cement with polymers | Sq.m | 674 |  | 0
6.16.04 | 40204 | Hand drilling in reinforced concrete | Lin.m | 651.6 |  | 0
6.16.05 | 40205 | Production and installation of steel parts and reinforcement | kg | 4947 |  | 0
6.16.06 | 40702 | Construction of expanssion joints to new decks (deck length less than 12 metres) | Lin.m | 628.98 |  | 0
6.16.07 | 40801 | Waterproofing to existing bridge decks | Sq.m | 14.6 |  | 0
6.16.08 | 40802 | Waterproofing to new bridge decks | Sq.m | 2464.3 |  | 0
6.16.09 | 40901 | Execution of metal safety parapets on the bridge deck | Lin.m | 280 |  | 0
6.16.10 | 40902 | Execution of metal safety parapets with stub foundation on the bridge deck | Lin.m | 197.6 |  | 0
6.16.11 | 40903 | Execution of metal safety parapets on the approach embankment | Lin.m | 274.68 |  | 0
6.16.12 | 40904 | Painting of the poles of metal safety parapets | Lin.m | 752.28 |  | 0
6.16.13 | 41203 | Protection to approach embankment slopes with reinforced concrete of 12 cm thicknes over a layer of crushed stone of 10 cm thickness | Sq. m | 241.5 |  | 0
6.16.14 | 41301 | Laying of 70 mm of fine asphalt Type A, M-I, on the carriageway of the bridge deck in two layers | Sq.m | 2040 |  | 0
6.16.15 | 41302 | Laying of 40mm of fine asphalt Type A, M-I, on the walkways | Sq.m | 515.5 |  | 0
6.16.16 | 41802 | Dismantling of the metal pedestrian parapets | Lin.m | 210 |  | 0
6.16.17 | 41804 | Removal of the asphalt pavement on the bridge deck | Sq. m | 2152 |  | 0
| Total to Bridges Summary |  |  |  |  | 0

## 7,Masuri contra def
Not Used

## 8,Indicat, marcaj cu schimb
8. Signs, Markings and Guardrail
Item No. | Specn. Ref | Description | Units | Quantitiy | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
8.01 | 70105 | Installation of road signs Type B - 700 | Number | 83 |  | 0
8.02 | 70105 | Installation of road signs Type D - 700 | Number | 6 |  | 0
8.03 | 70105 | Installation of road signs Type A- 900 | Number | 121 |  | 0
8.04 | 70105 | Installation of road signs 700x350 | Number | 4 |  | 0
8.05 | 70105 | Installation of road signs 600x900 | Number | 19 |  | 0
8.06 | 70105 | Installation of road signs 2250x500 | Number | 2 |  | 0
8.07 | 70105 | Installation of road signs 2200x500 | Number | 26 |  | 0
8.08 | 70105 | Installation of road signs 2100х1100 | Number | 4 |  | 0
8.09 | 70105 | Installation of road signs 2600х1500 | Number | 3 |  | 0
8.10 | 70103 | Installation of Kilometer posts | Number | 21 |  | 0
8.11 | 70104 | Installation of marker posts | Number | 760 |  | 0
8.12 | 70201 | Road marking Type 1.1.1; a continuous line of width 0.1 m | Sq.m. | 4990 |  | 0
8.13 | 70201 | Road marking Type 1.5; a discontinuous line with the ratio of segments and intervals 1:3, width 0.1 m | Sq.m. | 1188 |  | 0
8.14 | 70201 | Road marking Type 1.6; a discontinuous line with the ratio of segments and intervals 3:1, width 0.1 m | Sq.m. | 4 |  | 0
8.15 | 70201 | Road marking Type1.7 a discontinuous line with the ratio of segments and intervals 1:1, width 0.1 m | Sq.m. | 119 |  | 0
8.16 | 70201 | Road marking Type 1.8; |  | 75 |  | 0
8.17 | 70201 | 1.13 road marking | Sq.m. | 17 |  | 0
8.18 | 70201 | 1.14.1 road marking | Sq.m. | 108 |  | 0
8.19 | 70201 | 1.16.1 road marking | Sq.m. | 64 |  | 0
8.20 | 70201 | 1.16.2 road marking | Sq.m. | 40 |  | 0
8.21 | 70201 | 1.16.3 road marking | Sq.m. | 43 |  | 0
8.22 | 70201 | 1.18 road marking | Sq.m. | 88 |  | 0
8.23 | 70201 | 1.19 road marking | Sq.m. | 18 |  | 0
8.24 | 70201 | 1.20 road marking | Sq.m. | 20 |  | 0
8.25 | 70201 | 1.23 road marking | Sq.m. | 21 |  | 0
8.26 | 60101 | Install new galvanised steel Guard Rail type 11 DO MJ | Lin.m. | 1873 |  | 0
|  | Total Signs and Markings to Summary |  |  |  | 0

## 9, Drum later
9. Miscellaneous Works
9A, Side Roads, Junctions, Bus Iaybys, etc
Item No | Specn. Ref | Discription | Unit | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
9A.1 | 20104 | Excavation in all materials including slipped soil and benches with material transported to embankment or to spoil | Cu.m | 2371 |  | 0
9A.2 | 20106 | Shape and compact subgrade | Sq.m | 4823 |  | 0
9A.3 | 30201 | Regulating course of asphalt mixture | Tonnes | 1072 |  | 0
9A.4 | 30301 | Sand drainage layer | Cu.m | 1443 |  | 0
9A.5 | 30302 | Subbase courses of ballast or crushed limestone | Cu.m | 2462 |  | 0
9A.6 | 30303 | Base courses of crushed granite | Cu.m | 846 |  | 0
9A.7 | 30401 | Prime-coat using cutback bitumen | Litres | 12139 |  | 0
9A.8 | 30402 | Tack coat using cutback bitumen or bituminous emulsion | Litres | 6679 |  | 0
9A.9 | 30501 | Wearing course of asphalt concrete from fine grained dense asphalt Type A M1 thickness 40mm | Sq.m | 23918 |  | 0
9A.10 | 30504 | Base course made of fine grained porous asphalt concrete M1 Thickness 60mm | Sq.m | 11132 |  | 0
9A.11 | 30506 | Base course made of coarse grained porous asphalt concrete e M1 thickness 85mm | Sq.m | 3760 |  | 0
9A.12 | 40402 | Mounting of bridge deck slabs of reinforced concrete, 6,00 m span | unit | 14 |  | 0
9A.13 | 50110 | Construction of culverts (dia 600mm) at entrance to properties and side roads | Lin.m | 150 |  | 0
9A.14 | 50801 | Precast concrete kerbing and backing | Lin.m | 1130 |  | 0
Total Side Roads, Junctions, Bus Laybus To Miscellaneous Works Summary | [5 empty] | 0
9B, Property Accesses
Item No | Specn. Ref | Discription | Unit | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
9B.1 | 20105 | Excavate materials in Borrow pit and transport to site of embankment | Cu.m | 697 |  | 0
9B.2 | 20106 | Shape and compact subgrade | Sq.m | 3060 |  | 0
9B.3 | 30301 | Sand drainage layer | Cu.m | 306 |  | 0
9B.4 | 30302 | Subbase courses of crushed limestone | Cu.m | 459 |  | 0
9B.6 | 30402 | Tack coat using cutback bitumen or bituminous emulsion | Litres | 3060 |  | 0
9B.7 | 30501 | Wearing course of asphalt concrete from fine grained dense asphalt Type A M1 thickness 40mm | Sq.m | 3060 |  | 0
9B.8 | 40402 | Mounting of bridge deck slabs of reinforced concrete, 6,00 m span | unit | 86 |  | 0
9B.9 | 50110 | Construction of culverts (dia 600mm) at entrance to properties and side roads | Lin.m | 115 |  | 0
Total Property Accesses To Miscellaneous Works Summary | [5 empty] | 0
9C, Walkway
Item No | Specn. Ref | Discription | Unit | Quantity | Rate | Amount
0 | 1 | 2 | 3 | 4 | 5 | 6
9C.1 | 70301 | Repair of existing sidewalk with asphalt concrete | Sq.m | 8859 |  | 0
9C.2 | 70302 | Construction of new sidewalk with Asphalt concrete surface | Sq.m | 2206 |  | 0
|  | Total Walkway To Miscellaneous Works to Summary |  |  |  | 0
Miscellaneous Works Summary
|  | TOTAL for 9A: Side Roads, Junctions, Bus Laybus |  |  |  | 0
|  | TOTAL for 9B: Property Accesses |  |  |  | 0
|  | TOTAL for 9C: Walkway |  |  |  | 0
|  | Total Miscellaneous Works To Summary |  |  |  | 0

## 10. Dayworks
10. Schedule of Daywork Rates
Labour
Item | Pay Item | Description | Unit | Quantity | Rate | Amount
No. | No.
10.1L |  | Foreman/Ganger | hr. | 400 |  | 0
10.2L |  | Carpenter | hr. | 400 |  | 0
10.3L |  | Steelwork Erector | hr. | 400 |  | 0
10.4L |  | Mason | hr. | 400 |  | 0
10.5L |  | Bricklayer | hr. | 400 |  | 0
10.6L |  | Equipment Operator | hr. | 800 |  | 0
10.7L |  | Vehicle Operator | hr. | 800 |  | 0
10.8L |  | Mechanic | hr. | 800 |  | 0
10.9L |  | Assistant Mechanic | hr. | 400 |  | 0
10.10L |  | Skilled Labour | hr. | 1600 |  | 0
10.11L |  | Un-skilled Labour | hr. | 3000 |  | 0
|  |  | TOTAL for Daywork: Labour |  |  | 0
(Carried to Dayworks Summary)
10. Schedule of Daywork Rates
Materials
Item | Pay Item | Description | Unit | Quantity | Rate | Amount
No. | No.
10.1M |  | Concrete Culvert 600mm Diameter | Lin.m. | 20 |  | 0
10.2M |  | Concrete Culvert 900mm Diameter | Lin.m. | 20 |  | 0
10.3M |  | Concrete Culvert 1200mm Diameter | Lin.m. | 20 |  | 0
10.4M |  | Pvc Pipe 150mm diameter | Lin.m. | 200 |  | 0
10.5M |  | Pvc Pipe 100mm diameter (perforated) | Lin.m. | 200 |  | 0
10.6M |  | Cement | ton | 10 |  | 0
10.7M |  | Sand | ton | 20 |  | 0
10.8M |  | Aggregate | ton | 30 |  | 0
10.9M |  | Reinforcing Steel (High Yield) | ton | 4 |  | 0
10.10M |  | Formwork | Sq.m. | 200 |  | 0
10.11M |  | Concrete class B10 | Cu.m. | 10 |  | 0
10.12M |  | Concrete class B10 | Cu.m. | 10 |  | 0
10.13M |  | Concrete class B10 | Cu.m. | 10 |  | 0
10.14M |  | Concrete class B10 | Cu.m. | 10 |  | 0
10.15M |  | Concrete class B10 | Cu.m. | 10 |  | 0
|  |  | TOTAL for Daywork: Materials |  |  | 0
(Carried to Dayworks Summary)
10. Schedule of Daywork Rates
Equipment
Item | Pay Item | Description | Unit | Quantity | Rate | Amount
No. | No.
10.1E |  | Tracked Excavator, 10 ton | hr | 100 |  | 0
10.2E |  | Rubber Tyred Excavator, 10 ton | hr | 100 |  | 0
10.3E |  | Small Grader 120HP | hr | 200 |  | 0
10.4E |  | Backhoe Loader Large 4WD | hr | 100 |  | 0
10.5E |  | Front End Loader CAT 936 | hr | 100 |  | 0
10.6E |  | Tipper Trucks 4-6 m3 | hr | 400 |  | 0
10.7E |  | Air compressor (5250l/m) | hr | 200 |  | 0
10.8E |  | Flatbed Transport Truck 10 tons | hr | 100 |  | 0
10.9E |  | Water Bowser 10 tons | hr | 200 |  | 0
10.10E |  | Concrete Mixers (500l) | hr | 100 |  | 0
10.11E |  | Vibrating Plate Compactor | hr | 100 |  | 0
10.12E |  | Jackhammer | hr | 100 |  | 0
|  |  | TOTAL for Daywork: Equipment |  |  | 0
(Carried to Dayworks Summary)
|  | TOTAL for Daywork: Labour |  |  |  | 0
|  | TOTAL for Daywork: Materials |  |  |  | 0
|  | TOTAL for Daywork: Equipment |  |  |  | 0
|  | Total Dayworks carried to General Summary |  |  |  | 0